## BOQ
ITEM | DESCRIPTION | UNIT | QTY. | UNIT RATE | TOTAL PRICE
1. | Earth Works
1.1 | Excavation in all types of soil except rock from ground level to required depth, including dewatering, supporting excavation sides, and removal of surplus material and disposal off site to approved location. | m3 | 4200 | 85 | 357000
1.2 | Backfill with sand and/or selected excavated material as specified, compaction to Specification and satisfaction of the Engineer including all other necessary measures. | m3 | 2600 | 210 | 546000
2. | Concrete Works
2.1 | Plain concrete (C16/20) for foundation as per drawings and technical specifications. | m3 | 450 | 3510 | 1579500
2.2 | Plain concrete (C16/20) for roof slopes as per drawings and specifications. | m2 | 850 | 500 | 425000
2.3 | Reinforced concrete (C25/30), 150 mm thick for floor slabs including formwork & steel reinforcement all as per drawings and specifications. | m2 | 780 | 735 | 573300
2.4 | Reinforced concrete (C25/30) for foundations including formwork & steel reinforcement as per drawings and specifications. | m3 | 600 | 4850 | 2910000
2.5 | Reinforced concrete (C25/30) for columns and walls including formwork & steel reinforcement as per drawings and specifications. | m3 | 1350 | 5125 | 6918750
2.6 | Reinforced concrete (C25/30) including formwork & steel reinforcement for beams and slabs as per drawings and specifications. | m3 | 850 | 5200 | 4420000
3. | Protection Works
3.1 | Supply and install torch applied bituminous membrane sheets 4 mm thick for water proofing, For floor Including 50 mm screed layer. | m2 | 450 | 420 | 189000
3.2 | Supply and install torch applied bituminous membrane sheets 4 mm thick for water proofing, For roof & wet areas including 50 mm screed layer. | m2 | 850 | 420 | 357000
3.3 | Supply and apply three coats of protective coating using bituminous latex emulsion to face of concrete and walls adjacent to backfilling. | m2 | 1115 | 115 | 128225
4. | Heat Insulation
4.1 | 50 mm extruded polystyrene boards for roof heat insulation with minimum density 35 kg/cm | m2 | 850 | 400 | 340000
5. | Masonry Works
5.1 | Supply and install concrete hollow / solid blocks for walls Internal block walls 12 cm thickness, including all accessories for work completion. | m3 | 388 | 1025 | 397700
5.2 | Supply and install concrete hollow / solid blocks for walls External block walls 25 cm thickness, including all accessories for work completion. | m3 | 980 | 1025 | 1004500
5.3 | Supply and install concrete hollow / solid blocks for walls Sub Structure solid block work 25 cm thickness | m3 | 196 | 1125 | 220500
6. | Rendering Works
6.1 | Supply and apply Internal plastering to walls and ceilings, base and finish coat, thickness 20 mm. | m2 | 18236 | 85 | 1550060
6.2 | Supply and apply external cement plastering to facades, base and finish coat, thickness 15 mm striped with 2 cm groove render for facades & internal surface of parapet. | m2 | 4125 | 128 | 528000
7. | Painting Works
7.1 | Supply and apply 2 layers of acrylic paint over 2 coats of primer for all internal walls and ceilings to acceptance of the Engineer. | m2 | 16358 | 110 | 1799380
7.2 | Supply and applying 2 layers of external Acrylic paint over 2 coats of primer to the acceptance of the Engineer. | m2 | 3622 | 200 | 724400
8. | Tiling Works
8.1 | Supply and fix non-slip color porcelain floor tiles grade A , Spain, size 40x40x1cm as per specifications , drawings and supervisor engineer instructions. | m2 | 680 | 340 | 231200
8.2 | Supply and lay ceramic floor tiles 300 x 300 x 8 mm on 80 mm sand and cement sand mortar. | m2 | 1240 | 165 | 204600
8.3 | Supply and lay 6 mm thick ceramic wall tiles, with colours and dimensions according to drawings. | m2 | 800 | 165 | 132000
8.4 | Supply and lay 200 x 200 x 20 mm cement tiles for roofs including roof slopes and skirting. | m2 | 850 | 74 | 62900
8.5 | Supply and lay red granite 3 cm thick for entrance landing in accordance with the requirements of specifications and approval of Engineer. | m2 | 126 | 870 | 109620
9. | Doors & Windows
9.1 | Supply and install aluminium doors with frames, glazing, steel bars and mosquito mesh wire: a Door type (D3) with dimension 0.90 x 2.20 m with 6 mm glass panel. | No. | 38 | 3500 | 133000
9.2 | Supply and install aluminium windows with frames, glazing, steel bars and mosquito mesh wire: a Window type (W1) with dimension 1.50 x 1.20 m, 6mm glass. | No. | 64 | 2860 | 183040
10. | Metal Works
10.1 | Supply and fix Multi Lock door SD1 (100 x220x4cm),complete with galvanized steel frame 3mm thick, ironmongery, all requirement as latches, locks…etc. as per specifications, drawings and supervisor engineer instructions. | No. | 8 | 4500 | 36000
10.2 | Supply and install Galvanized Steel Grill for window type AW1 protection with all required works . | No. | 18 | 1800 | 32400
10.3 | Supply and install Galvanized Steel Handrail for stair landing with all required works | m | 95 | 44 | 4180
11. | Plumbing Works
11.1 | Sanitary Fixtures | L.S | 1 | 450000 | 450000
11.2 | Water Supply | L.S | 1 | 625000 | 625000
11.3 | Sanitary Installation | L.S | 1 | 382000 | 382000
11.4 | Fire Fighting Works | L.S | 1 | 84500 | 84500
11.5 | HVAC WORKs | L.S | 1 | 680500 | 680500
12. | Electrical Works
12.1 | Distribution Boards | No. | 6 | 22500 | 135000
12.2 | Lighting Fixtures and Switches | L.S | 1 | 315500 | 315500
12.3 | Sockets | L.S | 1 | 254110 | 254110
12.4 | Fire Alarm System | L.S | 1 | 175000 | 175000
12.5 | Telephone and Intercom systems | L.S | 1 | 168000 | 168000
12.6 | Earthing System | L.S | 1 | 45000 | 45000
13. | Site Layout
13.1 | Subgrade levelling and cleaning including cut & fill works to reach the subgrade design levels according to design drawings and project sepcifications, | m3 | 1350 | 55 | 74250
13.2 | Supply and install Colored Interlocking Tiles 6 cm thick (B-450)for theside works, size and shape as directed by the engineer or his representative. | m2 | 1210 | 320 | 387200
13.3 | Supply, laying and construct precast concrete kerbs (grade 25 with dimensions (15 x 30 x 50 cm) laid on concrete haunches and base using sulphate cement according to design drawings, project specifications and to the direction of the Engineer. | m | 850 | 160 | 136000
13.4 | Provide reinforced concrete pavement slabs for roads with widths and dimensions as shown in the design drawings | m2 | 612 | 2100 | 1285200
31294515
1. | Earth Works | 903000 |  | Earth Works | 903000 | 2.885%
2. | Concrete Works | 16826550 |  | Concrete Works | 16826550 | 53.77%
3. | Protection Works | 674225 |  | Finishing Works | 8367705 | 26.74%
4. | Heat Insulation | 340000 |  | Plumbing Works | 2222000 | 7.1%
5. | Masonry Works | 1622700 |  | Electrical Works | 1092610 | 3.491%
6. | Rendering Works | 2078060 |  | Site Layout | 1882650 | 6.016%
7. | Painting Works | 2523780 |  |  | 31294515 | 100%
8. | Tiling Works | 740320
9. | Doors & Windows | 316040
10. | Metal Works | 72580
11. | Plumbing Works | 2222000
12. | Electrical Works | 1092610
13. | Site Layout | 1882650
| Total | 31294515

## Project Data
|  | Project Name | New City
|  | Project Code: | M
|  | Start Date: | 2023-01-01
|  | Project Duration: | 12 Months
|  | Finish Date: | 2023-12-31
|  | 9 Buildings | GR+Three Floors
B .09 | 33% | 100
B .01 | 67% | 33.3333 | 66.6667
|  | 1 | 0.02
| 100% | B .01 | 13.33%
| 6.667% | B .02 | 13.33%
|  | B .03 | 13.33%
|  | B .04 | 13.33%
|  | B .05 | 13.33%
|  | B .06 | 6.667%
|  | B .07 | 6.667%
|  | B .08 | 13.33%
|  | B .09 | 6.667%
100%
|  | PREP. | 6%
|  | EX. | 90%
|  | Han | 4%

## Dashboard
New City - Follow Up
Report No. | Project Planned Start |  | Project Planned Finish |  | Project Duration |  | Planned Value | 11.44% | 88.56% | 3580841
R.02 | 2023-01-01 |  | 2023-12-31 |  | 365 |  | Earned Value | 7.74% | 92.26% | 2422758
Report Date | Project Total Value |  | No. of Variation Orders |  | SPI
2023-02-15 | 31294515 |  | 0 |  | 67.66% | [8 empty] | Activity ID | Activity Name | Original Duration | Start | Finish | Budgeted Total Cost | Remaining Total Cost | Earned Value Cost | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
[14 empty] | New City |  | 345 | 01-Jan-2023 A | 2023-12-31 | 31294515 | 28557066 | 2777314 | 3799945 | 6613277 | 9326305 | 12262606 | 14901077 | 17273522 | 22187139 | 25152750 | 28557066 | 28557066 | 28557066
Elapsed Duration | Planned Value |  | Earned Value |  | Variance | Invoices | Total Value | 31294515 | [13 empty] | 12.14% | 21.13% | 29.8% | 39.18% | 47.62% | 55.2% | 70.9% | 80.37% | 91.25% | 91.25% | 91.25%
| 3580841 |  | 2422758 |  | -3.7% |  | Invoices | 1850000 | [13 empty] | 21.01% | 30% | 38.67% | 48.05% | 56.49% | 64.07% | 79.77% | 89.24% | 100.1% | 100.1% | 100.1%
[22 empty] | 21.01% | 30% | 38.67% | 48.05% | 56.49% | 64.07% | 79.77% | 89.24% | 100.1% | 100.1% | 100.1%
45 |  | 11.44% |  | 7.74%
972758
[11 empty] | Spreadsheet Field | Planned % | Actual % | Recovery
[11 empty] | 2022-12-01 | 0% | 0%
[11 empty] | 2023-01-15 | 5.493% | 4%
[11 empty] | 2023-02-01 | 19.37% | 7.74%
[11 empty] | 2023-03-01 | 26.3% | 8.87% | 8.87%
[11 empty] | 2023-04-01 | 34.25% |  | 21.01%
[7 empty] | Elapsed Duration | 45 |  |  | 2023-05-01 | 42.45% |  | 30%
[7 empty] | Remaining | 320 |  |  | 2023-06-01 | 49.44% |  | 38.67%
[7 empty] | Total Durration | 365 |  |  | 2023-07-01 | 56.46% |  | 48.05%
[11 empty] | 2023-08-01 | 65.53% |  | 56.49%
[11 empty] | 2023-09-01 | 72.97% |  | 64.07%
[11 empty] | 2023-10-01 | 80.99% |  | 81%
[11 empty] | 2023-11-01 | 94.08%
[11 empty] | 2023-12-01 | 100%
[11 empty] | 2024-01-01 | 100%
[11 empty] | Spreadsheet Field | Planned | Actual
[11 empty] | 2023-01-01 | 1719152 | 1450000
[11 empty] | 2023-02-01 | 4343831 | 972785
[11 empty] | 2023-03-01 | 2167916
[11 empty] | 2023-04-01 | 2486578
[11 empty] | 2023-05-01 | 2567802
[11 empty] | 2023-06-01 | 2185897
[11 empty] | 2023-07-01 | 2197887
[11 empty] | 2023-08-01 | 2837977
[11 empty] | 2023-09-01 | 2327053
[11 empty] | 2023-10-01 | 2511091
[11 empty] | 2023-11-01 | 4095826
[11 empty] | 2023-12-01 | 1853504